## Slide 1: Fundamentals in Risk Management _2
IITA Risk Management Committee – May 2017

## Slide 2: CONTENTS
Recap (Why are we here, RM process, RM methods)
Risk Response /Treatment (Réponse / traitement des risques)
Risk Mitigation (Atténuation des risques)
Risk Reporting (Rapports sur les risques )
Risk Management at IITA today (Gestion des risques
à l'IITA aujourd'hui)
IITA topmost Risk 2016 (Risque maximal de l'IITA 2016 )
Expectation From Stakeholders (Attente des parties
prenantes)

## Slide 3: Why are we here?
Where and How do I fit
Where does your station fits
Your unit/project and you

## Slide 4: The Risk Management Process

## Slide 5: Risk Identification Methods
Brainstorm
Lesson Learnt
Interview
Statistical Analysis
Fault tree
Questionnaire

## Slide 6: Risk Responses/Treatment
A process to modify risk (ISO 31000)
What can & will we do about risk
Risk treatment (or response) involves:
• the selection of one or more options for modifying risks
• implementing those options
• the treatments then provide controls or modify current controls
Controls include any process, policy, device, practice or other actions which modify the risk
Events
Impact
Barriers
Likelihood
Mitigations
Risk

## Slide 7: Risk Mitigation
ACCEPT = take risk, tolerate
AVOID = eliminate uncertainty, terminate
TRANSFER = Involve others, share
REDUCE = change size, treat
Known Likelihood Known Consequence Q1 Risk-reward trade off | Known Likelihood Unknown Consequence Q3 Build in resilience, robustness
Unknown likelihood Known Consequence Q2 Proactive hazard management, protective systems and procedures | Unknown Likelihood Unknown Consequence Q4 Shift or exit where possible, be prepared
Current Risk
Eliminate, treat, or Tolerate
Reduce Consequence
Reduce likelihood

## Slide 8: Risk Mitigation

## Slide 9: Risk Mitigation Plan
A mitigation plans should include:
a description of the planned action o the expected benefit(s)
the performance measurements and constraints o accountabilities (risk and control owners)
reporting, monitoring & assessment requirements (including frequency)
resources required
timing and scheduling
Likely effectiveness of the control action
Risk | Mitigation Plan | Indicator | Time Line | Current Status | Lead/Responsible Person
Risk 1: Performance of project leads to Donor withdrawal of funds | Develop a project monitoring template | Project monitoring document/template developed Number of filled project monitoring templates | Template developed and available for project managers , coordinators, and scientists to request An ongoing activity, 17 projects/programs/units have filled the template. Also worked with 29 support units on their data matrices tool |  | DDG R4D,PAO, Program directors and M&E Specialist

## Slide 10: RISK REPORTING
Oversight
IITA Board of Trustees
Institute wide Risk Management
Management team
Identification of risk at micro level
Hub/ Station RMC
Coordination, analysis and reporting
Risk Management Committee

## Slide 11: Risk Reporting

## Slide 12: Risk Management at IITA Today
Risk management Policy
Risk management Committee
  Awareness Seminar
  Risk Register (Corporate level)
  Risk Awareness week
  Business Continuity plan
  Board reporting
Hub Level Risk management Committee
Risk Identification Template
Risk Assessment 2014 and 2016
Mitigation plan developed (2014)

## Slide 13: IITA Topmost Risk 2016
PROJECT DEVELOPMENT & CONTRACTUAL
Poor Project Execution due to delay in releasing funds and partners inability to; a) comply with contractual obligations;, b) deliver on assigned task, c) separate project funds from their other funds, d) demonstrate commitment and be more engaged
LOSS OF BIO-RESOURCES
Non-attainment of project deliverables due to loss of R4D resources, such as farm trials, soil and plant samples or germplasm, microbial collections, pest, diseases and farm destruction by animals
RESOURCE MOBILIZATION
Operational disruption arising from over dependence on resources from a few core donors;
INFORMATION AND COMMUNICATION TECHNOLOGY (ICT)
Loss of critical data due to failure of ICT system and policies and; Data Security and loss of sensitive information

## Slide 14: IITA Topmost Risk 2016
FINANCE & CONTROLS
Loss of liquid asset (Investment risk); Loss of outstanding payments from donors (Receivable risk); Loss of funds/ liquid asset due to operational inefficiency, Burglary/Forgery/Theft of cash and Risk associated with unsettled advances on Projects
LOSS OF CRITICAL INFRASTURUCTURE
Productivity loss due to infrastructural failure i.e. prolong power failure, breakdown of air conditional, water treatment plant, laboratory equipment, Road accident, inadequate office/lab accommodation, loss of vehicles , screen/glass house, malfunction of old equipment and natural disaster; Loss of Critical Infrastructure
HUMAN CAPITAL
Non adaptation of generic HR policies to local laws and non-specification of which legal jurisdiction apply to individual international staff contracts; Exit of critical staff / staff turnover; Human and financial loss due to occupational hazard; Recruitment/Employment Contract / Staffing Remuneration & Talent Management.

## Slide 15: IITA Topmost Risk 2016
POLITICAL & OTHERS
Operational disruption due to political unrest, insecurity, riots, unrests. (Station/campus vulnerability due to inadequate security infrastructure); Productivity loss due to our unique working environment i.e. Government Bureaucracy/delayed processing of shipping document, frequent vehicle breakdowns due to poor road infrastructure and long distances. erratic Fuel and power supply; Political & others.
MANAGEMENT/ADMINISTRATION
Poor management of change process which the Institute goes through almost every 4 years, leaves room for various speculations and confusion/blurring of roles; Management/Administration; Crisis of cohesion—The Management Team(MT); Strategic direction from the Board; Crisis of learning and accountability
LOSS OF CRITICAL INFRASTURUCTURE
Operation disruption due to challenges of supply chain system i.e. Lack of Procurement Plan, Delayed delivery of imported goods, scarcity and High cost and low quality of essential resources, late payment of suppliers; Loss of Resources

## Slide 16: IITA Topmost Risk 2016
SUPPLY CHAIN
Complications arising from unaligned and changing operational model in certain units i.e. Poor planning from programming unit and changing prices of supplies; Control risk at stations outside HQ; Potential reputational risk due to Genetically Modified Organism (GMO) protest, chemical spillage, improper handling of waste, Reputational loss due to non-compliance with regulatory laws; Reputational risk arising from evolving linkages among Research, Development and business; Loss of assets due to theft by stakeholders due to robbery, theft, accident
OPERATIONAL/REPUTATION/LEGAL
Station/campus vulnerability due to inadequate security infrastructure i.e. inefficient profiling at the gate
SECURITY
Station/campus vulnerability due to inadequate security infrastructure i.e. inefficient profiling at the gate,

## Slide 17: Moving Forward

## Slide 18: Expectations from stakeholders
Unit level
All team members
Identify the risks in your activities
Day-to-day activities
Your mitigating and monitoring strategies for identified risks
Report to RMC in your locality
Individual level
Participate in Unit’s Risk Identification Process
Be proactive
Ask questions when carrying out your duties
What, When, Where and Way Out of the potential risks identified

## Slide 19: Expectations from stakeholders
Get involved
Be proactive
Understand the Risk Assessment/Management Process
Participate in Unit/Project Risk Identification and assessment
Ask questions when carrying out your duties
What , When, Where and Way Out of the potential risks identified

## Slide 20: Expectations from stakeholders
Continuously identify the risk in your areas
Determine their likelihood of occurring
Determine the severity of impact
Ascertain controls currently in place
Identify what else can or needs to be done
Create a Unit/Lab/field level Risk Register
Take actions identified
Monitor effect of the actions taken and
Revise Risk Register