A multiple donor, multi location and multi year projects

Objectives and Outcomes

| Vision of Success | To raise average grain legumes yields by 954 kg/ha in four legumes (groundnut, cowpea, soybean, and common bean), increase average biological nitrogen fixation (BNF) by 46 kg/ha, and increase average household income by $465, directly benefiting 225,000 households (1,800,000 individuals) in eight countries in sub-Saharan Africa (DRC, Ghana, Kenya, Malawi, Mozambique, Nigeria, Rwanda, Zimbabwe). Indeed, this project links the protein and nitrogen needs of poor African farmers directly to previously inaccessible, massive atmospheric reserves, provides them with new income-generating crop production enterprises, presents a mechanism of renewable soil fertility management and opens the door to the adoption of numerous, profitable accompanying farm technologies and value-adding enterprises. |
| --- | --- |

| Objective 1 | Establish a baseline of the current status of N2-fixation, identify niches for targeting N2-fixing legumes in the impact zones, M&E and impact assessment |  |
| --- | --- | --- |
| Activities | Outputs | Outcomes |
| 1.1 Establish project management structures | - By month 3 of year 1 a general project inception meeting held. - By month 2 of year 1 the project steering committee is constituted. - By month 6 of year 1 project staff engaged and capital investments made in all impact zones. - By month 12 of year 4 a synthesis document on project achievements produced following a cross-regional synthesis meeting. | An efficient, responsive project management structure is established, project staff recruited, advance project planning conducted and mechanisms for project findings developed. |
| 1.2 Develop planning documents and identify the project sites within the impact zones. | - By month 2 of year 1 hold TL-II meeting. -By month 3 of year 1 at least 10 action sites identified in the West-African millet-sorghum-livestock, the West, East and southern African maize-livestock, and the Central African cassava-maize impact zones. - By month 6 of year 1 detailed country plans for extension, P access, seed systems and marketing submitted for approval to BMGF - By month 6 of year 1 a project interaction plan with AGRA developed | Specific locations and farmer groups identified for field studies and follow-up technology dissemination actions. The project will work directly with 225,000 farm households over four years; 18000 in year one, 24000 in year two, 51,000 in year three and 132000 in year four. |
| 1.3 Identify new opportunities for targeting legume and inoculant technologies to increase BNF and enlarge the production areas of prioritized grain legumes. | - By month 6 of year 1 at least 2 priority legume and inoculant technologies have been identified for each impact zone. - By month 6 of year 2 a complete market analysis for inoculum in representative areas of the three hubs including cost/benefit analysis at smallholder level; recommendations for private sector engagement. - By month 10 of year 2 a document on market demand for legumes linking with TL-II and AGRA in SSA. - By month 6 of years 2,3&4 tested opportunities are identified prior to each following cropping season. | Key BNF technologies, legume enterprises and production strategies are identified and advanced through the N2fixAfrica project. |
| 1.4 Quantify the current on-farm N2-fixation in the target farming systems and its impact on livelihoods (income, nutrition). | - By month 6 of year 1 a background document characterizing (e.g., climate, population, soil type) the target impact zones based upon secondary data and project field work is available to all partners. - By month 12 of year 1 a baseline report quantifying the current level of BNF and its contributions to rural livelihoods is available for all impact zones. | A baseline report is issued that documents current BNF and legume production levels, identifies production constraints within impact zones, prioritizes planned interventions and their expected household and market impacts and presents a detailed project work plan. |
| 1.5 Monitor impact of investments and uptake of legume and inoculant technologies in the impact zones. | - By month 6 of year 1 indicators for monitoring and evaluating progress with project activities and their impact are developed through stakeholder participation. - By month 3 of years 2,3&4 a monitoring and evaluation framework has been used for evaluating progress and planning subsequent activities during planning workshops - By month 6 of year 3 an external project review has been conducted, with representatives of the Bill & Melinda Gates Foundation. | Project guidelines for monitoring and evaluation are published and distributed to all project partners, annual assessment of project activities issued through published reports and web sites, external project reviews are conducted and project strategies and activities are adjusted as required. Project goals are measured against indicators of success and baseline conditions and reported through papers submitted to leading journals. |
| 1.6 Evaluate the impact of introduced legume and inoculant technologies on farmer’s livelihoods [income, health, productivity] and soil health in the impact zones. | - By month 12 of year 4 a comprehensive published report on the impact of N2-fixation technologies and grain legume enterprises on farmers’ livelihoods is produced. | Findings on rural livelihood and soil health are published in leading developmental journals and used to facilitate policy formulation on legume and inoculant technologies in eight countries. National programs and developmental organizations invest in similar projects within additional countries. |

| Objective 2 | Select multi-purpose legumes providing food, animal feed, structural materials and high quality crop residues for enhanced BNF and integrate improved varieties into farming systems |  |
| --- | --- | --- |
| Activities | Outputs | Outcomes |
| 2.1. Select best varieties of soybean and common beans for high N2-fixation capacity and adaptation to abiotic [low soil P, soil acidity, etc] and biotic stresses [pests and diseases]. | - By month 6 of year 1, at least 3 existing soybean and common bean varieties with proven high BNF potential and sufficient seed availability identified for the respective impact zones. - By month 12 of year 2 three new soybean and common bean breeding materials with high BNF traits identified and tested, and then by month 12 of year 3 forwarded to TLII and other breeding initiatives for inclusion in their respective programs. - By month 12 of year 4, at least 3 farmer-accepted lines each of soybean with high BNF potential identified through farmer participatory variety selection for the respective impact zones and submitted to national release committees in at least 4 countries. | Five elite soybean varieties with high BNF potential and farmer-accepted agronomic characteristics, along with their accompanying specialized legume inoculants are widely available to farmers through community-based, developmental and commercial channels. |
| 2.2 Select best varieties of common beans for higher N2-fixation capacity and adaptation to abiotic and biotic stress conditions. | - By month 6 of year 1, at least 3 existing common bean varieties with proven higher BNF potential and sufficient seed availability identified for the respective impact zones. - By month 12 of year 3 three new common bean breeding materials with high BNF traits identified and tested, and then forwarded to TLII and other breeding initiatives for inclusion in their respective programs. - By month 12 of year 4, at least 3 farmer-accepted lines of common bean with high BNF potential identified through farmer participatory variety selection for the respective impact zones and submitted to national release committees in at least 4 countries. | Five elite common beans elite varieties with high BNF potential and farmer-accepted agronomic characteristics, along with their accompanying specialized legume inoculants are widely available to farmers through community-based, developmental and commercial channels. |
| 2.3. Select cowpea and groundnut varieties with high N2-fixation capacity and adaptation to abiotic and biotic stress conditions. | - By month 6 of year 1, at least 3 existing cowpea and groundnut varieties with proven high BNF potential, tolerant to biotic and abiotic stresses, and sufficient seed availability identified for the respective impact zones. - By month 12 of year 3, cowpea and groundnut breeding materials with high BNF traits forwarded to TLII and other breeding initiatives for inclusion in their respective breeding programs. - By month 12 of year 4, at least 5 farmer-accepted lines of cowpea and groundnut varieties with high BNF potential and tolerant to biotic and abiotic stresses identified through farmer participatory variety selection for the respective impact zones and submitted to national release committees in at least 4 countries. | Six groundnut elite varieties and 3 cowpea elite varieties, and their accompanying specialized legume inoculants are widely available to farmers through community-based, developmental and commercial channels. |
| 2.4. Explore the N2-fixing potential of multi-purpose forage legumes for intensive meat and milk production and environmental services. | - By month 12 of year 1 four forage legumes with high BNF capacity have been identified across the 3 impact zones and by month 12 of year 2, sufficient planting materials is available for widespread farmer testing. - By month 12 of year 4 a detailed report on forage legume performance within the impact zones is published | Four improved lines of multipurpose green manure/forage legumes with high N2-fixation capacity are widely available to farmers through community-based, developmental and commercial channels. |
| 2.5. Identify best-fit agronomic practices (system design, need for amendments) for maximizing potential benefits of legume and inoculant technologies on increasing and stabilizing productivity. | - By month 6 of year 2, at least 9 adaptive [research campaigns focusing on major gain legume (soybean, common bean, cowpea, groundnut) implemented in the 3 impact zones. - By month 12 of year 4, at least 9 applied research activities focusing on fodder legumes have been implemented in 3 impact zones. | Proven agronomic guidelines supporting cereal-legume intercropping and rotation within three major agro-ecological zones of Africa are published and distributed to farming, developmental and research organizations. |
| 2.6 Evaluate contributions of best fit agronomic practices to system productivity and livelihoods with specific attention to trade-off analysis between competing enterprises. | - By month 12 of year 3, household benefits from specific BNF interventions quantified for the major grain legumes in 3 impact zones. - By month 12 of year 4, household benefits from specific BNF interventions quantified for the other legumes in 3 impact zones. | The potential roles of at least ten different nitrogen-fixing legumes within farming households in Africa are described in both technical and popular terms and these food, fodder and tree legumes are better targeted within future rural development programs. |

| Objective 3 | Select superior rhizobia strains for enhanced BNF and develop inoculum production capacity in sub-Saharan Africa, including private sector partners |  |
| --- | --- | --- |
| Activities | Outputs | Outcomes |
| 3.1 Assess the need-to-inoculate for the target legumes and identify elite strains across the impact zones. | - By month 6 of year 1, protocols for nodule sampling, rhizobia isolation, characterization, evaluation for BNF, competitiveness and persistence are updated and standardized. - By month 12 of year 1, at least 400 soil rhizobial counts (MPN) and accompanying need-to-inoculate trials conducted for soybean and beans, representing existing soil heterogeneity in 3 impact zones. - By month 6 of year 3, at least 2,000 strains screened for effectiveness under greenhouse conditions to select the top 5% for field testing. - By month 12 of year 3, the benefits of inoculation of soybean and beans with at least 2% of the elite strains demonstrated in 4 impact zones. - By month 12 of year 4, at least 5 new elite rhizobial strains that significantly increase BNF over the standard strain in production are distributed to inoculant manufacturers. | Findings and recommendations on legume inoculation from different research laboratories are more accurately interpreted and widely extrapolated through the use of tested, accepted and published standardized methods. Forty strains of elite, well-characterized rhizobia are available to the worldwide research community for inclusion within programs designed to optimize BNF, resulting in more accurate and efficient developmental research. Five superior strains of rhizobia are mass produced by legume inoculant manufacturers resulting in greater returns to investment in inoculation technology by African farmers. |
| 3.2 Establish and characterize a rhizobium germplasm bank in the impact zones. | - By month 9 of year 1, elite strains of rhizobia are obtained from leading inoculant producers and rhizobiology laboratories worldwide. - By month 4 of year 2, at least 10 nodules of soybean and beans collected in at least 200 sites in 3 impact zones, for isolate characterization and inclusion in the germplasm bank. | The biodiversity of rhizobia in Africa is described and well-characterized rhizobial isolates maintained by multiple laboratories as a future genetic resource. |
| 3.3 Formulate improved inoculant products and develop cost-effective production methods, including quality assurance procedures. | - By month 6 of year 1, quality assurance (QA) protocols are developed, based on African capacities and international existing standards. - By month 12 of year 2, cost effective inoculant production methods including fermentation technologies, carrier selection, inoculant formulation, enhanced shelf life are developed. - By month 6 of year 3, universal logo representing project QA standards developed and in use within cooperating laboratories. | The cost of inoculant manufacture is lowered and the efficacy of inoculation products is improved, resulting in more affordable and higher quality inoculants that are distributed through better targeted production and marketing strategies. |
| 3.4 Expand and upgrade inoculant production capacity in sub-Saharan Africa. | - By month 6 of year 1, information on existing inoculant plants, their production capacity, range and availability and quality of products is documented. - By month 12 of year 1, existing rhizobiology laboratories upgraded. - By month 6 of year 2, at least 50,000 inoculant packets produced per year in at least 4 cooperating laboratories, increasing in years 3&4. - By month 6 of year 1, 2 & 3 potential private sector innoculant producers will be invited to a planning meeting and interim assessment workshops. By month 12 of year 4, strategic alliances established between private sector and research centers for inoculant production and use. | Short-term inoculant manufacturing capacity among current producers is increased by at least 200,000 packets per year resulting in improved BNF within 80,000 ha By the end of the project, inoculant production is passed to private sector manufactures and subject to free market forces. |
| 3.5 Conduct and advocate policy review on inoculant quality and cross border movement. | - By month 12 of year 3, at least 3 policy briefs related to legume and inoculant regulation and cross-border trade produced per impact zone. - By month 12 of year 4, procedures for exchange of, and access to, bacterial strains are developed. | Policymakers are better informed on importance of inoculant product regulation and trans-boundary movement, resulting in a more facilitating manufacturing and marketing environment. |

| Objective 4 | Deliver legume and inoculant technologies to farmers throughout sub-Saharan Africa |  |
| --- | --- | --- |
| Activities | Outputs | Outcomes |
| 4.1. Create strategic alliances for facilitating dissemination of legume and inoculant technologies in the impact zones. | - By month 6 of year 1, Memoranda of Understanding are formalized with key partners along the legume value chains in the impact zones. - By month 8 of year 1, the role of AGRA and other partners in the project defined (helps AGRA-SHP) and co-funding/financing options for scale-up of inoculum (banks, AGRA, industry) identified. - By month 12 of year 3, at least 10 additional satellite sites have been identified per impact zone. | A coordinated alliance of researchers, development specialists, farmer associations and entrepreneurs accelerates the deployment of key BNF technologies, generating demand for proven new products and advocating for legume-based enterprises and their associated benefits. |
| 4.2. Produce specific dissemination tools, including inoculant packets, adapted to the needs of farmer groups, agro-dealers, and development partners. | - By month 6 of years 2,3&4, at least new 1 dissemination tool related to legume and inoculant use are produced per impact zone, resulting in about 24 different tools by the middle of year 3. | An array of extension materials are adopted by national programs and development organizations across sub-Saharan Africa, facilitating their future operations and directing them toward BNF-based approaches. |
| 4.3. Engage with other legume seed production and marketing activities, farm input, commodity marketing and processing initiatives, and household and children’s nutrition programs operating throughout the impact zones. | - By month 12 of year 1, sufficient [several tons] legume seed is acquired, e.g., through cooperation with TL-II and the private sector, for initial dissemination in the various impact zones. - By month 6 of year 2, at least half of the farming communities engaged in the project are actively producing seed for local distribution. - By month 12 of year 2, at least half of the farming communities engaged in the project are actively linked to legume market outlets. - By month 12 of year 3, at least half of the farming communities engaged in the project are linked to legume processing initiatives. | Farming technologies developed through this project find immediate application within existing rural development activities and their benefits more quickly reach a wider range of stakeholders |
| 4.4. Conduct collaborative legume and inoculant technology dissemination campaigns and create awareness in rural communities in all impact zones. | - By month 10 of year 1, a dissemination and extension process and proof of principle (pilot-testing) documented. - By month 6 of each year, large scale demonstration and dissemination campaigns launched in each impact zone. - By month 9 of each year, at least 3 extension events (e.g., field days, exchange visits) organized per season per country. - By month 12 of each year, at least 3 mass media events (e.g., radio programs, video documentaries) organized per hub. | Over four years, 225,000 farming households will participate in technology dissemination activities providing a nucleus for farmer-to-farmer adoption and creating sufficient demand to reinforce private sector investment in legume and inoculant technologies. |
| 4.5. Develop strategies for empowering women to benefit from the project products. | - By month 6 of year 2, gender analysis in relation to specific legumes, labor, preferences documented. - By month 9 of year 2,3&4, a report documenting the involvement of women in at least 50% of all farmer-related activities, where relevant, produced. - By month 12 of each year, at least 2 special events on the role of legumes in household nutrition and value-added processing conducted per country. | Family nutrition improves and new value-addition and marketing opportunities emerge permitting more balanced gender empowerment at the household and community levels. |

| Objective 5 | Develop and strengthen capacity for BNF research, technology development, and application |  |
| --- | --- | --- |
| Activities | Outputs | Outcomes |
| 5.1 Provide short-term, high level technical training for project scientific and technical staff in essential microbiological skills and BNF technologies. | - By month 9 of year 1, at least 4 technical staff from the 3 hubs trained on inoculant production and quality control, lab-based PCR methods, N2 fixation quantification, and associated laboratory, greenhouse, and field techniques. - By month 9 of years 2,3&4, annual short courses and master classes conducted to upgrade skills and expertise for at least 90 [3 years x 3 hubs x 10 people] key technical staff from the 3 impact zones. | More and better trained laboratory and field technicians are positioned to produce greater amounts of higher quality legume inoculants and seed of improved varieties of legumes. |
| 5.2 Advanced training to MSc and PhD level of an elite young cadre of African scientists focused on topics filling identified knowledge gaps and identified through competitive calls. | - By month 6 of year 1, at least 14 MSc and 6 PhD candidates divided among three hubs selected for training. - By month 12 of year 3, at least 10 MSc candidates graduated. - By month 12 of year 4, the remaining MSc and 6 PhD candidates graduated. | Graduate studies explore less obvious opportunities to advance BNF within African farming systems and their most important findings are incorporated into larger project activities. More and better trained African scientists pursue practical research goals that contribute to the state-of-the-art for many years into the future. |
| 5.3 Training-of-trainers workshops on legume and inoculant technologies for agricultural extension workers and NGO staff. | - By month 10 of year 1, at least 1 training of ‘master’ trainers workshops conducted in Nairobi and attended by 24 ‘master’ trainers (6 per impact zone), on inoculation technology (inoculant handling and storage, etc) and legume agronomy. - By month 10 of years 2 and 3, at least 8 training-of-trainers workshops (2 workshops in each country), attended by at least 40 extension staff, conducted on inoculation technology (inoculant handling and storage, etc) and legume agronomy [resulting in 640 trainers by the end year 3]. | Extension agents and other key dissemination agents provide more accurate advice and explanations to farmers in areas related to BNF and legume-based enterprises. Capacities for a stepwise amplification of technical training is established, tested and documented, providing a useful model for rapid future instruction in BNF technologies and other needed areas |
| 5.4 Training workshops on legume and inoculant technologies for agro-dealers and officers of farmer associations and community-based organizations. | - By month 12 of year 2,3&4, at least 1 grass-root training event organized by each of 51 trainers across all impact zones, with an expected attendance of 10 master farmers or community facilitators per event [resulting in 93,000 farmers trained by the end of year 3]. - By month 12 of year 4, at least 1 grass-root training event organized by each of 81 new trainers across all impact zones, with an expected attendance of 10 master farmers or community facilitators per event [resulting in 132,000 additional farmers trained by the end of year 4]. - By month 12 of years 2,3&4, at least 30 agro-dealers in each hub are trained in accessing, managing and distributing information on inoculant use, resulting in 270 trained agro-dealers by the end of the fourth year. | Demand for legume and inoculant products is increased and better met by agro-dealers and their farm input supply networks. Adoption of legume and inoculant technologies within community-based organizations is accelerated through better understanding of BNF and legume-based enerprises. |
| 5.5 Provide training, educational and extension resource materials to support activities 5.1 – 5.4. | - By month 9 of year 1, a revised manual for rhizobium methods and standard protocols available on the project website (www.N2fixAfrica.net). - By month 12 of year 3, BNF resource materials provided to 25 African Universities through the Regional Universities FORUM and the African Association of Biological Nitrogen Fixation (AABNF) to assist in course development and instruction. - By month 3 of year 3, training programs will organized in collaboration with selected private sector partners in each of the mandate zones for various categories of staff in key aspects of inoculant production and quality control. - By month 12 of year 3&4, web-based support will be provided on key N2 fixation methodologies and techniques, including the development of an interactive learning tool describing BNF, the infection process and legume root nodulation. | Educational and learning materials developed in support of N2fixAfrica will assist project staff and reach other related programs and organizations, raising understanding and practical skills in legume and inoculation technologies. Members of AABNF become reoriented toward more practical problem solving approaches through the example provided by N2fixAfrica. |